## Task Tracker
GroSpace — Production Build Task Sheet (3-Engineer Sprint)
Team: Adi (UI/Frontend) · Aryan (Backend/AI) · Uday Jit (Infra/DevOps/Testing) ¦ Duration: 5 Weeks ¦ Goal: Production-Grade SaaS
PRD v1.0 ¦ Proposal v1.0 ¦ Client: Srabhjot Singh (GroSpace Global)
# | Week | Owner | Category | Task | Description / Acceptance Criteria | Priority | Days | Status | Dependencies / Notes
WEEK 1 — PRODUCTION HARDENING & INFRASTRUCTURE (Parallel across all 3 engineers)
1 | W1 | Aryan | Backend | Background job system (pg_cron / Edge Functions) | Create 4 scheduled jobs: (1) alert-engine — hourly scan obligations & key dates, generate alerts with configurable lead times; (2) payment-status-updater — daily mark overdue payments; (3) escalation-calculator — daily check upcoming escalations, recalculate amounts; (4) email-digest — daily 8AM IST. Deploy via Supabase pg_cron or Edge Functions. | P0 | 3 | Not Started | #1 production gap — no background automation
2 | W1 | Aryan | Backend | Wire email sending via Resend | Install resend SDK. Create email templates: (1) daily digest (overdue, due today, coming this week), (2) single alert notification. Add RESEND_API_KEY to .env. Wire dispatch_notification() to actually send. Test with real emails. | P0 | 2 | Not Started | Needs Resend account + API key
3 | W1 | Aryan | Backend | Agreement & outlet auto-status transitions | In daily cron: (1) agreements within X days of lease_expiry_date → "expiring", (2) past expiry → "expired", (3) outlets with expiring lease → "up_for_renewal". X = configurable per org (default 90 days). | P1 | 1 | Not Started | Depends on Task 1 (cron)
4 | W1 | Aryan | Backend | Wrap confirm-and-activate in DB transaction | confirm-and-activate does 5+ inserts (outlet, agreement, obligations, alerts, documents). Wrap in Supabase RPC or begin/commit. If any insert fails, roll back all. Log to activity_log. | P0 | 1 | Not Started | Partial state currently possible
5 | W1 | Aryan | Backend | Add file size validation (50MB max) + type check | Validate file size in /api/upload-and-extract before processing. Reject >50MB with 413. Validate file type (PDF, JPG, PNG only). Return clear error messages. | P1 | 0.5 | Not Started | PRD specifies 50MB max
6 | W1 | Uday Jit | Security | Restrict CORS + rate limiting + demo creds | Replace allow_origins=['*'] with [FRONTEND_URL, 'https://grospace.vercel.app']. Install slowapi for rate limiting: upload (5/min), qa (20/min), extract (10/min). Move demo creds to env vars (DEMO_EMAIL, DEMO_PASSWORD). | P0 | 1 | Not Started | Security hardening — all quick wins
7 | W1 | Uday Jit | Database | Run migration_004 on production Supabase | Run supabase/migration_004_deal_pipeline.sql on prod via SQL Editor. Verify: deal_stage column on outlets, showcase_tokens table, alert_preferences on organizations, activity_log table. | P0 | 0.5 | Not Started | Required for pipeline & showcase to work
8 | W1 | Uday Jit | DevOps | Set up GCP service account for Cloud Vision | In Google Cloud Console: (1) Enable Cloud Vision API, (2) Create service account with roles/visionai.user, (3) Download JSON key, (4) Add GOOGLE_APPLICATION_CREDENTIALS to Railway env vars, (5) Test with scanned PDF upload. | P1 | 0.5 | Not Started | Required for Cloud Vision OCR to work
9 | W1 | Uday Jit | Database | Create Supabase RPC for portfolio Q&A | Create exec_readonly_sql(query_text text) RPC function. Validate query starts with SELECT. Apply org_id filtering. Return results as JSONB array. Run on production Supabase. | P1 | 0.5 | Not Started | Required for portfolio Q&A to work
10 | W1 | Adi | Frontend | Add error boundaries to all routes | Create error.tsx files in: app/, app/outlets/[id]/, app/agreements/[id]/, app/pipeline/, app/payments/, app/reports/, app/settings/. Show friendly error message with retry button. Log errors to console. | P1 | 1 | Not Started | React pages crash on API errors currently
11 | W1 | Adi | Frontend | Loading states & skeleton improvements | Audit all pages for missing loading states. Add proper skeleton loaders to: outlet detail, agreement detail tabs, alerts list, payments table, pipeline board. Ensure no layout shift on data load. | P1 | 1 | Not Started | UX polish — perceived performance
12 | W1 | Adi | Frontend | Mobile responsiveness pass | Test all pages on 375px/414px viewports. Fix: sidebar collapse on mobile (hamburger menu), table horizontal scroll, card stacking, modal sizing, pipeline board horizontal scroll, form layouts. Use Tailwind responsive prefixes (sm:/md:/lg:). | P1 | 2 | Not Started | Many pages break on mobile
13 | W1 | Adi | Frontend | Toast notifications for all mutations | Add sonner/react-hot-toast. Show success/error toasts for: upload, confirm & activate, payment update, alert acknowledge/snooze, outlet update, settings save, showcase create. Replace alert() calls. | P1 | 1 | Not Started | No user feedback on actions currently
WEEK 2 — NOTIFICATION CENTER & CORE UI FEATURES
14 | W2 | Adi | Frontend | Build notification center (bell icon + dropdown) | PRD 4.6.3: Bell icon in top-bar with unread count badge. Click opens slide-out Sheet panel. Group notifications: Today ¦ This Week ¦ Earlier. Each item: alert type icon, outlet name, brief message, time ago. Click navigates to relevant page. Mark as read on click. Fetch from GET /api/alerts?status=pending. | P0 | 2 | Not Started | Major PRD gap — users have no passive notification
15 | W2 | Adi | Frontend | Split-screen extraction review UI | PRD 4.1.3: After AI extraction, show split view — PDF viewer on left (scrollable, zoomable via react-pdf), extracted fields on right organized by section (collapsible). Each field: label, value (editable input), confidence badge (green/yellow/red/grey dot). Low-confidence fields auto-expanded. Add 'Save as Draft' button alongside 'Confirm & Activate'. | P1 | 2.5 | Not Started | Currently sequential steps, not side-by-side
16 | W2 | Adi | Frontend | Dashboard enrichment — 5 new widgets | PRD 4.7.1: Add: (1) Expiring Leases next 90d — count + list, (2) Expiring Licenses next 90d, (3) Risk Flags summary by severity, (4) Outlets by model type (FOFO/FOCO/COCO), (5) Outlets by property type. Each widget clickable → filtered view. | P1 | 2 | Not Started | Dashboard has basic stat cards only
17 | W2 | Adi | Frontend | Role-scoped dashboard views | PRD 4.7.1-4.7.3: Platform Admin sees all orgs, Org Admin sees own org, Org Member sees 'My outlets' + due this week + overdue + upcoming. Add role check, filter API calls by role, different widget sets per role. | P1 | 1 | Not Started | Same dashboard for all roles
18 | W2 | Aryan | Backend | Add 'Save as Draft' endpoint | PATCH /api/agreements/{id}/save-draft — saves extracted_data and risk_flags without creating obligations/alerts. Sets extraction_status='review'. User can return later to confirm. Show draft agreements with 'Review' badge. | P1 | 0.5 | Not Started | Currently only Confirm & Activate exists
19 | W2 | Aryan | Backend | Enforce role permissions matrix (PRD 4.9.2) | Add middleware/decorator: Org Members cannot create outlets, edit agreements, assign alerts, export reports. Org Admins cannot create organizations. Return 403 for unauthorized actions. Reference PRD permissions table. | P1 | 1 | Not Started | Backend only checks org membership
20 | W2 | Aryan | Backend | Dashboard stats endpoint — add new fields | Extend GET /api/dashboard response: expiring_licenses_90d, risk_flags_by_severity, outlets_by_model_type, outlets_by_property_type, upcoming_escalations_90d, overdue_payment_total. Scope by org_id and role. | P1 | 1 | Not Started | Needed for Adi Task 16
21 | W2 | Aryan | Backend | Notification read/unread tracking | Add is_read boolean to alerts table. GET /api/alerts?unread_only=true for notification center. PATCH /api/alerts/{id}/read to mark as read. GET /api/alerts/unread-count for badge number. | P1 | 0.5 | Not Started | Needed for Adi Task 14
22 | W2 | Uday Jit | Testing | Backend unit tests — core business logic (pytest) | Write pytest tests for: (1) extraction pipeline (mock Gemini, verify JSON schema), (2) obligation generation from sample extraction, (3) alert generation with lead times, (4) payment status logic, (5) role permissions. Target: 80% coverage on core logic. Add pytest + pytest-asyncio to requirements.txt. | P1 | 3 | Not Started | Zero tests currently
23 | W2 | Uday Jit | Infra | Set up Sentry monitoring (backend + frontend) | Backend: add sentry-sdk, initialize in main.py, add @sentry_sdk.trace to AI endpoints. Enhance /api/health to check: Supabase connection, Gemini API, storage bucket. Frontend: install @sentry/nextjs, configure in next.config.mjs. Add SENTRY_DSN to both .env files. | P1 | 1 | Not Started | No error monitoring currently
24 | W2 | Uday Jit | Infra | CI/CD pipeline — GitHub Actions | Create .github/workflows/ci.yml: (1) On PR: lint (eslint) + type-check (tsc) + backend lint (ruff). (2) On merge to main: auto-deploy frontend to Vercel, backend to Railway via webhooks. Add test step once tests exist. | P1 | 1 | Not Started | Manual deploys only
WEEK 3 — REPORTING, PAYMENTS, WHATSAPP & OUTLET VIEWS
25 | W3 | Adi | Frontend | Complete reports table — all 16 PRD columns | PRD 4.8.1: Add missing columns: Days to Expiry, Revenue (last month), Rent-to-Revenue %, Risk Flags count, Overdue Amount. Add multi-filter: brand, city, property type, model type, status, lease expiry range (date picker), has overdue, has risk flags. All columns sortable. CSV export with applied filters. | P1 | 2 | Not Started | Currently basic table
26 | W3 | Adi | Frontend | Bulk 'Mark all as Paid' + payment calendar | PRD 4.5.2: Add 'Mark all as Paid for this month' button. Confirmation dialog with obligation list. Calls batch PATCH. Add payment calendar view (monthly grid with obligation status colors). | P2 | 1.5 | Not Started
27 | W3 | Adi | Frontend | Rent-to-revenue color coding + outlet card view | PRD 4.2.3: Color code rent-to-revenue ratio: green (<12%), yellow (12-18%), red (>18%). Show on outlet cards. PRD 4.2.2: Add card view toggle on outlets list. Cards: name, brand, city, status, metrics, revenue input, alerts count. | P2 | 2 | Not Started
28 | W3 | Adi | Frontend | Agreement timeline visualization | PRD 4.3.2: Horizontal date bar on agreement detail: LOI signed → Lease commencement → Rent commencement → Lock-in expiry → Escalation dates → Lease expiry. Highlight current position. Flag upcoming events in amber. | P2 | 1 | Not Started
29 | W3 | Aryan | Backend | WhatsApp integration via MSG91 | Wire MSG91 WhatsApp Business API. Create template messages: rent_due, lease_expiry, escalation_coming, license_expiry. Read whatsapp_number from org notification_preferences. dispatch_notification() sends to configured channels. Add MSG91 env vars. | P0 | 2 | Not Started | Needs MSG91 account + Meta template approval (~2-5 days)
30 | W3 | Aryan | Backend | Hybrid MGLR auto-calculation | PRD 4.4.3: For hybrid_mglr: MGLR = mglr_per_sqft × super_area, Revenue share = (dine_in_pct × dine_in_revenue) + (delivery_pct × delivery_revenue), Rent payable = MAX(MGLR, Revenue share). Show which was higher. Create reconciliation obligation for difference. | P2 | 1.5 | Not Started | Needs revenue input
31 | W3 | Aryan | Backend | Configurable alert lead times per org | PRD 4.6.2: Each org configures lead times per alert type (e.g., lease_expiry: 180, 90, 30, 7 days). Store in org alert_preferences. Alert engine cron reads these. Default lead times per PRD table. | P1 | 1 | Not Started | Currently hardcoded
32 | W3 | Aryan | Backend | Reports API — add missing fields + filters | Extend GET /api/reports: days_to_expiry, last_month_revenue, rent_to_revenue_pct, risk_flags_count, overdue_amount. Add query params: brand, city, property_type, model_type, status, expiry_from, expiry_to, has_overdue, has_risk_flags. | P1 | 1 | Not Started | Needed for Adi Task 25
33 | W3 | Uday Jit | Testing | Frontend E2E tests (Playwright) | Install Playwright. Write E2E tests: (1) Login → Dashboard loads, (2) Upload PDF → Review → Confirm → Outlet created, (3) Outlet detail → all tabs, (4) Pipeline drag, (5) Alerts acknowledge/snooze, (6) Q&A chat. Add to CI. | P1 | 2 | Not Started
34 | W3 | Uday Jit | Infra | Set up staging environment | Create staging branch. Set up: Supabase staging project (clone schema), Railway staging service, Vercel preview deployment for staging branch. Document staging vs production env var differences. | P2 | 1.5 | Not Started | No staging environment
35 | W3 | Uday Jit | Database | Database backup + RLS audit | Verify Supabase Point-in-Time Recovery enabled. Document backup procedures. Audit all tables for proper RLS policies: outlets, agreements, obligations, alerts, payment_records, profiles, organizations. Ensure org_id scoping on all tables. | P1 | 1 | Not Started | Security critical
WEEK 4 — POLISH, REFACTORING & ADVANCED FEATURES
36 | W4 | Adi | Frontend | Settings page — alert preferences UI | PRD 4.6.2: In settings, add tab for alert preferences. Per alert type: toggle enabled/disabled, set lead time days (multi-select chips: 180, 90, 60, 30, 14, 7 days), choose notification channels (email, whatsapp, in-app). Save to org alert_preferences. | P1 | 1.5 | Not Started
37 | W4 | Adi | Frontend | Onboarding flow for new organizations | When org has 0 outlets: guided wizard — (1) Welcome screen, (2) Upload first agreement, (3) Review & confirm extraction, (4) Dashboard with data. Progress indicator. Skip option. Store onboarding_complete in org. | P2 | 1.5 | Not Started | Currently just empty state card
38 | W4 | Adi | Frontend | Dark mode support | Add dark mode toggle in settings/header. Use Tailwind dark: classes. Update all components: cards, tables, modals, charts, badges. Persist preference in localStorage. Auto-detect system preference. | P2 | 1.5 | Not Started | Nice-to-have for demos
39 | W4 | Adi | Frontend | Accessibility pass (WCAG 2.1 AA) | Audit: keyboard navigation on all interactive elements, ARIA labels on icons/buttons, color contrast ratios (4.5:1 min), focus indicators, screen reader support on data tables, form labels. Fix top issues. | P2 | 1 | Not Started
40 | W4 | Aryan | Backend | Split backend into modules | Refactor backend/main.py (~3K lines) into: routes/auth.py, routes/documents.py, routes/outlets.py, routes/agreements.py, routes/payments.py, routes/alerts.py, routes/pipeline.py, routes/showcase.py, routes/reports.py, routes/qa.py. Shared: services/supabase.py, services/gemini.py, services/notifications.py, models/. | P2 | 2 | Not Started | Tech debt — single monolith file
41 | W4 | Aryan | Backend | Bulk upload improvements | PRD 4.1.2: Add progress tracking per file in bulk upload. Return partial results (don't fail entire batch on one file error). Add retry mechanism for failed files. Show per-file status: processing, completed, failed. | P2 | 1 | Not Started
42 | W4 | Aryan | Backend | API response caching (Redis / in-memory) | Cache expensive endpoints: /api/dashboard (60s TTL), /api/reports (120s TTL), /api/pipeline (30s TTL). Use lru_cache or Redis. Invalidate on write operations. Add cache-control headers. | P2 | 1 | Not Started | Performance optimization
43 | W4 | Aryan | Backend | Audit logging for all mutations | Log to activity_log table on every create/update/delete: who (user_id), what (entity_type, entity_id), action (created, updated, deleted), changes (JSON diff), timestamp. Show in agreement/outlet detail pages. | P1 | 1 | Not Started | Compliance requirement
44 | W4 | Uday Jit | DevOps | Deployment runbook + README | Write comprehensive deployment guide: Supabase setup (schema, extensions, RLS, storage), Railway backend config, Vercel frontend config, DNS setup, env vars checklist, rollback procedures. Update README with local dev setup. | P1 | 1 | Not Started
45 | W4 | Uday Jit | Testing | Load testing + performance baseline | Use locust or k6 to load test: /api/upload-and-extract (concurrent uploads), /api/dashboard, /api/qa, /api/portfolio-qa. Document: response times at 10/50/100 concurrent users, identify bottlenecks, set performance budgets. | P2 | 1 | Not Started
46 | W4 | Uday Jit | Infra | SSL, custom domain, and security headers | Configure custom domain on Vercel + Railway. Verify SSL. Add security headers: X-Content-Type-Options, X-Frame-Options, Strict-Transport-Security, Content-Security-Policy. Verify HTTPS redirect. | P1 | 1 | Not Started
47 | W4 | Uday Jit | Testing | Full regression test + bug bash | End-to-end manual testing of all features. Create test case checklist. Log all bugs found. Prioritize P0/P1 fixes. Re-test after fixes. Sign off on production readiness. | P1 | 2 | Not Started | Final QA before launch
WEEK 5 — AI ENHANCEMENTS & LAUNCH PREP (ALREADY BUILT: Tasks 48-52)
48 | W5 | Aryan | Backend/AI | Google Cloud Vision OCR integration | extract_text_cloud_vision() for scanned PDFs. Cloud Vision → text → Gemini text path (cheaper). Gemini vision as fallback. extraction_method="cloud_vision" in response. | P1 | 1 | Done | GOOGLE_APPLICATION_CREDENTIALS needed
49 | W5 | Aryan | Backend/AI | Enhanced single-doc Q&A with sessions | session_id on QARequest. Conversation history via document_qa_sessions table. Last 10 messages in prompt. Clause citations (blockquotes). Cloud Vision OCR text for scanned doc Q&A. | P1 | 1.5 | Done | Uses existing document_qa_sessions table
50 | W5 | Aryan | Backend/AI | Cross-portfolio Q&A endpoint | POST /api/portfolio-qa. Natural language → Gemini SQL generation → SELECT only → execute → natural language answer. Schema-aware prompting. org_id scoping. | P1 | 1.5 | Done | Needs exec_readonly_sql RPC (Task 9)
51 | W5 | Adi | Frontend | Enhanced Q&A chat panel — agreement detail | session_id persistence, conversation history, blockquote citations, "Clear conversation" button, 4 suggested question chips. | P1 | 1 | Done
52 | W5 | Adi | Frontend | Portfolio Q&A widget — dashboard | PortfolioQA component: input field, suggested question chips, expandable message history, data table rendering (max 10 rows), loading state. | P1 | 1 | Done
53 | W5 | Adi | Frontend | Q&A — suggested follow-up questions | After AI response, show 2-3 AI-generated follow-up question chips based on the answer. Backend returns suggested_questions in response. User can click to ask next question instantly. | P2 | 1 | Not Started | UX enhancement
54 | W5 | Aryan | Backend/AI | Document comparison endpoint | POST /api/compare-documents: accept 2 agreement_ids. Gemini compares extracted_data and highlights: rent differences, term differences, clause differences, missing clauses. Return structured diff. | P2 | 1.5 | Not Started | Phase 2 PRD feature
55 | W5 | Uday Jit | DevOps | Production launch checklist + go-live | Final checklist: all env vars set, migrations run, RLS verified, Sentry active, CI green, staging tested, backup verified, DNS propagated, SSL valid, rate limits active. Coordinate go-live. | P0 | 1 | Not Started | LAUNCH DAY
TOTAL DAYS
ENGINEER WORKLOAD SUMMARY
| Adi |  |  |  |  | Days:
| Aryan |  |  |  |  | Days:
| Uday Jit |  |  |  |  | Days:

## Weekly Plan by Engineer
GroSpace — Weekly Plan by Engineer
WEEK 1
Day | Adi (UI/Frontend) | Aryan (Backend/AI) | Uday Jit (Infra/DevOps)
Day 1 | Error boundaries + toast setup | Background jobs (pg_cron) — Day 1/3 | CORS + rate limiting + demo creds
Day 2 | Loading skeletons + states | Background jobs — Day 2/3 | Run migration_004 + GCP setup
Day 3 | Mobile responsiveness — Day 1/2 | Email sending (Resend) | Create portfolio Q&A RPC function
Day 4 | Mobile responsiveness — Day 2/2 | Transaction safety + file validation | Week 1 integration testing
Day 5 | Toast notifications + polish | Auto status transitions + testing | Week 1 integration testing
WEEK 2
Day | Adi (UI/Frontend) | Aryan (Backend/AI) | Uday Jit (Infra/DevOps)
Day 1 | Notification center — Day 1/2 | Save as Draft endpoint + Role perms | Backend unit tests — Day 1/3
Day 2 | Notification center — Day 2/2 | Dashboard stats + notification tracking | Backend unit tests — Day 2/3
Day 3 | Split-screen review — Day 1/2.5 | Role permissions middleware | Backend unit tests — Day 3/3
Day 4 | Split-screen review — Day 2/2.5 | Dashboard stats endpoint | Sentry monitoring setup
Day 5 | Dashboard widgets + role views | Week 2 bug fixes | CI/CD pipeline (GitHub Actions)
WEEK 3
Day | Adi (UI/Frontend) | Aryan (Backend/AI) | Uday Jit (Infra/DevOps)
Day 1 | Reports table — Day 1/2 | WhatsApp (MSG91) — Day 1/2 | Playwright E2E tests — Day 1/2
Day 2 | Reports table — Day 2/2 | WhatsApp (MSG91) — Day 2/2 | Playwright E2E tests — Day 2/2
Day 3 | Bulk payments + calendar | MGLR auto-calculation | Staging environment setup
Day 4 | Outlet card view + rent coloring | Configurable alert lead times | Database backup + RLS audit
Day 5 | Agreement timeline viz | Reports API — missing fields/filters | Staging environment testing
WEEK 4
Day | Adi (UI/Frontend) | Aryan (Backend/AI) | Uday Jit (Infra/DevOps)
Day 1 | Settings — alert preferences UI | Split backend into modules — Day 1/2 | Deployment runbook + README
Day 2 | Onboarding flow wizard | Split backend — Day 2/2 | Load testing (locust/k6)
Day 3 | Dark mode — Day 1/1.5 | Bulk upload improvements | SSL + custom domain + headers
Day 4 | Dark mode + a11y pass | API caching + audit logging | Regression test — Day 1/2
Day 5 | Accessibility fixes + polish | Audit logging + bug fixes | Regression test — Day 2/2
WEEK 5
Day | Adi (UI/Frontend) | Aryan (Backend/AI) | Uday Jit (Infra/DevOps)
Day 1 | Q&A chat panel (DONE) | Cloud Vision OCR (DONE) | Production launch checklist
Day 2 | Portfolio Q&A widget (DONE) | Q&A sessions (DONE) | Final staging verification
Day 3 | Follow-up question chips | Portfolio Q&A (DONE) | Go-live coordination
Day 4 | Final UI polish + fixes | Document comparison endpoint | Post-launch monitoring
Day 5 | Bug fixes + handoff | Bug fixes + handoff | Bug fixes + handoff

## Environment Variables
GroSpace — Environment Variables Reference
FRONTEND (.env.local)
Variable | Service | Description | Example Value | Status
NEXT_PUBLIC_SUPABASE_URL | Frontend | Supabase project URL | https://xxxxx.supabase.co | EXISTING
NEXT_PUBLIC_SUPABASE_ANON_KEY | Frontend | Supabase anonymous/public key | eyJhbGci... | EXISTING
NEXT_PUBLIC_API_URL | Frontend | Backend API URL (Railway) | https://grospace-backend.up.railway.app | EXISTING
NEXT_PUBLIC_APP_URL | Frontend | Frontend app URL (Vercel) | https://grospace.vercel.app | EXISTING
NEXT_PUBLIC_DEMO_EMAIL | Frontend | Demo login email (move from hardcoded) | admin@grospace.com | NEW
NEXT_PUBLIC_DEMO_PASSWORD | Frontend | Demo login password (move from hardcoded) | admin2025 | NEW
NEXT_PUBLIC_SENTRY_DSN | Frontend | Sentry DSN for error monitoring | https://xxx@xxx.ingest.sentry.io/xxx | NEW
BACKEND (.env)
Variable | Service | Description | Example Value | Status
SUPABASE_URL | Backend | Supabase project URL | https://xxxxx.supabase.co | EXISTING
SUPABASE_SERVICE_ROLE_KEY | Backend | Supabase service role key (SECRET) | eyJhbGci... | EXISTING
GEMINI_API_KEY | Backend | Google Gemini API key | AIza... | EXISTING
FRONTEND_URL | Backend | Frontend URL for CORS | https://grospace.vercel.app | EXISTING
PORT | Backend | Server port (Railway auto-sets) | 8000 | EXISTING
GOOGLE_APPLICATION_CREDENTIALS | Backend | Path to GCP service account JSON for Cloud Vision API | /path/to/service-account.json | NEW
RESEND_API_KEY | Backend | Resend API key for email sending | re_xxxxxxxxxxxx | NEW
RESEND_FROM_EMAIL | Backend | Verified sender email for Resend | alerts@grospace.com | NEW
MSG91_AUTH_KEY | Backend | MSG91 authentication key for WhatsApp | your-msg91-authkey | NEW
MSG91_SENDER_ID | Backend | MSG91 sender ID (6 chars) | GROSPC | NEW
SENTRY_DSN | Backend | Sentry DSN for backend error monitoring | https://xxx@xxx.ingest.sentry.io/xxx | NEW
ALLOWED_ORIGINS | Backend | Comma-separated CORS origins | https://grospace.vercel.app,http://localhost:3000 | NEW
SUPABASE (Dashboard Config)
Item | Service | Description | How to Configure | Status
pg_cron extension | Supabase | Required for background jobs | Database → Extensions → Search 'pg_cron' → Enable | NEW
exec_readonly_sql RPC | Supabase | Required for portfolio Q&A | SQL Editor → Create function (see migration) | NEW
Storage: documents bucket | Supabase | File storage (50MB max) | Storage → documents → Settings | VERIFY
Realtime: alerts table | Supabase | Enable realtime for notifications | Database → alerts → Enable Realtime | OPTIONAL
THIRD-PARTY ACCOUNTS
Service | Service | Purpose | Setup Notes | Status
Resend | Email | Transactional emails | resend.com — Free: 3K emails/mo. Verify domain DNS. | NEW
MSG91 | WhatsApp | WhatsApp Business API | msg91.com — Requires Meta business verification (~2-5 days) | NEW
Sentry | Monitoring | Error tracking | sentry.io — Free: 5K errors/mo. Create 2 projects. | NEW
Google Cloud | AI/OCR | Cloud Vision API for OCR | console.cloud.google.com — Enable Vision API + service account | NEW
Railway | Hosting | Backend hosting | railway.app — Verify auto-deploy enabled | EXISTING
Vercel | Hosting | Frontend hosting | vercel.com — Verify auto-deploy enabled | EXISTING

## PRD Gap Tracker
GroSpace — PRD Gap Tracker (Phase 1 + Phase 2)
4.1 Document Intelligence
PRD Ref | Gap | Status | Planned | Task # | Owner
4.1.1 | File size validation (50MB) | PARTIAL | W1 | 5 | Aryan
4.1.2 | Bulk upload progress tracking | PARTIAL | W4 | 41 | Aryan
4.1.3 | Split-screen review UI | MISSING | W2 | 15 | Adi
4.1.3 | Save as Draft option | MISSING | W2 | 18 | Aryan
4.1.3 | Low-confidence fields auto-expanded | PARTIAL | W2 | 15 | Adi
4.1.4 | Q&A conversation persistence | DONE | W5 | 49 | Aryan
4.1.4 | Q&A clause citations | DONE | W5 | 49 | Aryan
4.1.x | Google Cloud Vision OCR | DONE | W5 | 48 | Aryan
4.2 Outlet Master
PRD Ref | Gap | Status | Planned | Task # | Owner
4.2.1 | Auto status transitions | MISSING | W1 | 3 | Aryan
4.2.2 | Card view toggle on outlets list | MISSING | W3 | 27 | Adi
4.2.3 | Rent-to-revenue color coding | MISSING | W3 | 27 | Adi
4.3 Agreement Management
PRD Ref | Gap | Status | Planned | Task # | Owner
4.3.1 | Auto status transitions | MISSING | W1 | 3 | Aryan
4.3.2 | Agreement timeline visualization | MISSING | W3 | 28 | Adi
4.4 Obligation Engine
PRD Ref | Gap | Status | Planned | Task # | Owner
4.4.2 | Escalation auto-recalculation (cron) | MISSING | W1 | 1 | Aryan
4.4.3 | Hybrid MGLR MAX calculation | MISSING | W3 | 30 | Aryan
4.5 Payment Tracker
PRD Ref | Gap | Status | Planned | Task # | Owner
4.5.2 | Bulk 'Mark all Paid' | MISSING | W3 | 26 | Adi
4.5.2 | Payment calendar view | MISSING | W3 | 26 | Adi
4.6 Alert Engine
PRD Ref | Gap | Status | Planned | Task # | Owner
4.6.1 | Background alert generation (cron) | MISSING | W1 | 1 | Aryan
4.6.2 | Configurable lead times per org | PARTIAL | W3 | 31 | Aryan
4.6.3 | Notification center (bell icon) | MISSING | W2 | 14 | Adi
4.6.4 | Email digest sends | MISSING | W1 | 2 | Aryan
4.6.x | WhatsApp notifications | MISSING | W3 | 29 | Aryan
4.7 Dashboard
PRD Ref | Gap | Status | Planned | Task # | Owner
4.7.1 | Expiring leases/licenses widgets | MISSING | W2 | 16 | Adi
4.7.1 | Risk flags summary widget | MISSING | W2 | 16 | Adi
4.7.1 | Outlets by model/property type | MISSING | W2 | 16 | Adi
4.7.2-3 | Role-scoped dashboard views | MISSING | W2 | 17 | Adi
4.7.x | Portfolio Q&A (cross-doc chat) | DONE | W5 | 50-52 | Aryan+Adi
4.8 Reporting
PRD Ref | Gap | Status | Planned | Task # | Owner
4.8.1 | All 16 PRD columns | PARTIAL | W3 | 25 | Adi
4.8.1 | Multi-filter support (8 filters) | MISSING | W3 | 25 | Adi
4.8.1 | CSV export with filters | PARTIAL | W3 | 25 | Adi
4.9 Multi-Tenancy & Roles
PRD Ref | Gap | Status | Planned | Task # | Owner
4.9.2 | Role permissions enforcement | PARTIAL | W2 | 19 | Aryan
4.9.x | RLS audit on all tables | PARTIAL | W3 | 35 | Uday Jit
Non-Functional / Production
PRD Ref | Gap | Status | Planned | Task # | Owner
NFR | Error boundaries all routes | MISSING | W1 | 10 | Adi
NFR | Mobile responsiveness | PARTIAL | W1 | 12 | Adi
NFR | Error monitoring (Sentry) | MISSING | W2 | 23 | Uday Jit
NFR | CI/CD pipeline | MISSING | W2 | 24 | Uday Jit
NFR | Backend unit tests | MISSING | W2 | 22 | Uday Jit
NFR | E2E tests | MISSING | W3 | 33 | Uday Jit
NFR | Backend modularization | MISSING | W4 | 40 | Aryan
NFR | Load testing | MISSING | W4 | 45 | Uday Jit
NFR | Dark mode | MISSING | W4 | 38 | Adi
NFR | Accessibility (WCAG 2.1) | MISSING | W4 | 39 | Adi

## Engineer Profiles
GroSpace — Engineer Roles & Responsibilities
| Adi (UI/Frontend) | Aryan (Backend/AI) | Uday Jit (Infra/DevOps/QA)
Focus | All UI components, pages, UX flows, responsiveness, accessibility, design system | FastAPI backend, AI/ML (Gemini, Cloud Vision), business logic, data models, APIs | Infrastructure, CI/CD, testing (unit + E2E), security, monitoring, database, deployments
Tech Stack | Next.js 14, React, Tailwind CSS, shadcn/ui, Lucide icons, recharts, react-pdf | Python, FastAPI, Gemini 2.5 Pro, Cloud Vision API, Supabase SDK, Pydantic | GitHub Actions, Playwright, pytest, Sentry, Supabase (SQL, RLS, pg_cron), Railway, Vercel
Key Files | src/app/**/*.tsx, src/components/**/*.tsx, src/lib/api.ts | backend/main.py, backend/requirements.txt, backend/routes/*.py | .github/workflows/*.yml, supabase/*.sql, tests/**/*
Week 1 | 5 tasks (error boundaries, loading, mobile, toasts) | 5 tasks (cron jobs, email, transactions, auto-status, validation) | 4 tasks (CORS, migration, GCP setup, RPC function)
Week 2 | 4 tasks (notification center, split-screen review, dashboard, role views) | 4 tasks (save draft, role perms, dashboard API, notification tracking) | 3 tasks (pytest tests, Sentry, CI/CD)
Week 3 | 4 tasks (reports table, bulk payments, outlet cards, timeline) | 4 tasks (WhatsApp, MGLR, alert config, reports API) | 3 tasks (Playwright E2E, staging env, DB backup/RLS)
Week 4 | 4 tasks (settings UI, onboarding, dark mode, a11y) | 4 tasks (backend split, bulk upload, caching, audit log) | 4 tasks (runbook, load test, SSL/domain, regression)
Week 5 | 3 tasks (Q&A chat DONE, portfolio Q&A DONE, follow-ups) | 3 tasks (Vision OCR DONE, Q&A sessions DONE, doc comparison) | 1 task (production launch)