## Task Tracker
GroSpace — Production Build Task Sheet
Engineer: Aryan ¦ Duration: 4 Weeks ¦ Goal: Production-Grade SaaS
PRD v1.0 ¦ Proposal v1.0 ¦ Client: Srabhjot Singh (GroSpace Global)
# | Week | Category | Task | Description / Acceptance Criteria | Priority | Est Days | Status | Notes
WEEK 1 — PRODUCTION HARDENING & INFRASTRUCTURE
1 | Week 1 | Infrastructure | Set up background job system (pg_cron / Edge Functions) | Create 4 scheduled jobs: (1) alert-engine — hourly scan of obligations & key dates, generate new alerts with configurable lead times; (2) payment-status-updater — daily mark overdue payments; (3) escalation-calculator — daily check upcoming escalations, recalculate amounts; (4) email-digest — daily 8AM IST. Deploy via Supabase pg_cron or Edge Functions. | P0 CRITICAL | 3 | Not Started | This is the #1 production gap
2 | Week 1 | Infrastructure | Wire email sending via Resend | Install resend SDK in backend. Create email templates: (1) daily digest (overdue, due today, coming this week, key dates this month), (2) single alert notification. Add RESEND_API_KEY to .env. Wire dispatch_notification() to actually send. Test with real email addresses. | P0 CRITICAL | 2 | Not Started | Add RESEND_API_KEY to backend .env
3 | Week 1 | Security | Restrict CORS to production domains | Replace allow_origins=['*'] in backend/main.py with explicit list: [FRONTEND_URL, 'https://grospace.vercel.app']. Move demo credentials to env vars. Add DEMO_EMAIL and DEMO_PASSWORD to frontend .env. | P0 CRITICAL | 0.5 | Not Started
4 | Week 1 | Security | Add rate limiting to AI endpoints | Install slowapi or fastapi-limiter. Rate limit: /api/upload-and-extract (5/min/user), /api/qa (20/min/user), /api/extract (10/min/user). Return 429 with retry-after header. | P1 HIGH | 0.5 | Not Started
5 | Week 1 | Backend | Add file size validation (50MB max) | Validate file size in /api/upload-and-extract before processing. Reject >50MB with clear error. Also validate file type (PDF, JPG, PNG only). Return 413 for oversized files. | P1 HIGH | 0.5 | Not Started | PRD specifies 50MB max
6 | Week 1 | Backend | Wrap confirm-and-activate in DB transaction | The confirm-and-activate endpoint does 5+ separate inserts (outlet, agreement, obligations, alerts, documents). Wrap in a Supabase RPC or use begin/commit. If any insert fails, roll back all. Log transaction result to activity_log. | P0 CRITICAL | 1 | Not Started | Partial state currently possible
7 | Week 1 | Backend | Agreement status auto-transitions | In the daily cron job: (1) active agreements within X days of lease_expiry_date → 'expiring', (2) past lease_expiry_date → 'expired', (3) outlets with expiring lease → 'up_for_renewal'. X = configurable per org (default 90 days). Also auto-transition outlet status: operational → up_for_renewal. | P1 HIGH | 1 | Not Started
8 | Week 1 | Frontend | Add error boundaries to all routes | Create error.tsx files in: app/, app/outlets/[id]/, app/agreements/[id]/, app/pipeline/, app/payments/, app/reports/, app/settings/. Show friendly error message with retry button. Log errors to console (Sentry integration later). | P1 HIGH | 0.5 | Not Started | React pages crash on API errors currently
9 | Week 1 | Database | Run migration_004 on Supabase | Run supabase/migration_004_deal_pipeline.sql on the production Supabase project via SQL Editor. Verify: deal_stage column on outlets, showcase_tokens table created, alert_preferences column on organizations. Also verify activity_log table exists. | P0 CRITICAL | 0.5 | Not Started | Required for pipeline & showcase to work
WEEK 2 — NOTIFICATION CENTER & PHASE 1 COMPLETION
10 | Week 2 | Frontend | Build notification center (bell icon + dropdown) | PRD 4.6.3: Bell icon in top-bar with unread count badge. Click opens slide-out panel. Group notifications: Today ¦ This Week ¦ Earlier. Each item: alert type icon, outlet name, brief message, time. Click navigates to relevant page. Mark as read on click. Fetch from GET /api/alerts with status=pending. | P0 CRITICAL | 2 | Not Started | Major PRD gap — users have no passive notification
11 | Week 2 | Frontend | Split-screen extraction review UI | PRD 4.1.3: After AI extraction, show split view — PDF viewer on left (scrollable, zoomable via react-pdf), extracted fields on right organized by section (collapsible). Each field: label, value (editable), confidence badge (green/yellow/red/grey). Low-confidence fields auto-expanded. Add 'Save as Draft' button alongside 'Confirm & Activate'. | P1 HIGH | 2 | Not Started | Currently sequential steps, not side-by-side
12 | Week 2 | Backend | Add 'Save as Draft' endpoint | PATCH /api/agreements/{id}/save-draft — saves extracted_data and risk_flags without creating obligations/alerts. Sets extraction_status='review'. User can return later to confirm. Show draft agreements in agreement list with 'Review' badge. | P1 HIGH | 0.5 | Not Started | Currently only Confirm & Activate exists
13 | Week 2 | Frontend | Dashboard enrichment — expiring leases & licenses widgets | PRD 4.7.1: Add widgets: (1) Expiring Leases next 90 days — count + scrollable list, (2) Expiring Licenses next 90 days, (3) Risk Flags summary — count by severity (High/Medium), (4) Outlets by model type (FOFO/FOCO/COCO pie chart), (5) Outlets by property type. Each widget clickable → navigates to filtered view. | P1 HIGH | 2 | Not Started | Dashboard currently has basic stat cards only
14 | Week 2 | Frontend | Role-scoped dashboard views | PRD 4.7.1-4.7.3: Platform Admin sees all orgs, Org Admin sees own org only, Org Member sees 'My outlets' + due this week + overdue + upcoming alerts. Add role check in dashboard page. Filter API calls by role. Show different widget sets per role. | P1 HIGH | 1 | Not Started | Same dashboard for all roles currently
15 | Week 2 | Frontend | Agreement timeline visualization | PRD 4.3.2: Visual horizontal date bar on agreement detail page showing: LOI signed → Lease commencement → Rent commencement → Lock-in expiry → Escalation dates → Lease expiry. Highlight current position. Flag upcoming events in amber. Use extracted dates from agreement. | P2 MEDIUM | 1 | Not Started
16 | Week 2 | Backend | Enforce role permissions matrix (PRD 4.9.2) | Add middleware/decorator that checks role before allowing: Org Members cannot create outlets, edit agreements, assign alerts, export reports. Org Admins cannot create organizations. Return 403 for unauthorized actions. Reference PRD permissions matrix table. | P1 HIGH | 1 | Not Started | Backend currently only checks org membership
WEEK 3 — REPORTING, PAYMENTS & WHATSAPP
17 | Week 3 | Frontend | Complete reports table — all 16 PRD columns | PRD 4.8.1: Add missing columns to reports table: Days to Expiry, Revenue (last month), Rent-to-Revenue %, Risk Flags count, Overdue Amount. Add multi-filter support: brand, city, property type, model type, outlet status, lease expiry range (date picker), has overdue (yes/no), has risk flags (yes/no). All columns sortable. CSV export with applied filters. | P1 HIGH | 2 | Not Started | Currently basic table only
18 | Week 3 | Frontend | Bulk 'Mark all as Paid' on payments | PRD 4.5.2: Add button 'Mark all as Paid for this month' on payments page. Shows confirmation dialog with list of obligations to be marked. Calls batch PATCH endpoint. Also add payment calendar view (monthly grid showing obligations with status colors). | P2 MEDIUM | 1 | Not Started
19 | Week 3 | Backend | WhatsApp integration via MSG91 | Wire MSG91 WhatsApp Business API. Create template messages for: rent_due, lease_expiry, escalation_coming, license_expiry. Read whatsapp_number from org notification_preferences. dispatch_notification() sends to configured channels. Add MSG91_AUTH_KEY and MSG91_SENDER_ID to .env. Test with real WhatsApp number. | P0 CRITICAL | 2 | Not Started | Add MSG91_AUTH_KEY, MSG91_SENDER_ID to .env
20 | Week 3 | Frontend | Rent-to-revenue color coding on outlet cards | PRD 4.2.3: On outlet list and detail pages, color code rent-to-revenue ratio: green (<12%), yellow (12-18%), red (>18%). Show ratio prominently on outlet cards. Also add card view toggle on outlets list page (currently table only). | P2 MEDIUM | 0.5 | Not Started
21 | Week 3 | Backend | Hybrid MGLR auto-calculation | PRD 4.4.3: For hybrid_mglr rent model, calculate monthly: MGLR = mglr_per_sqft × super_area, Revenue share = (dine_in_pct × dine_in_revenue) + (delivery_pct × delivery_revenue), Rent payable = MAX(MGLR, Revenue share). Show which was higher. If revenue share > MGLR, create reconciliation obligation for the difference. | P2 MEDIUM | 1.5 | Not Started | Needs revenue input to be functional
22 | Week 3 | Backend | Configurable alert lead times per org | PRD 4.6.2: Allow each org to configure lead times for each alert type (e.g., lease_expiry: 180, 90, 30, 7 days). Store in org alert_preferences. Alert engine cron reads these values. Default lead times per PRD table if not configured. | P1 HIGH | 1 | Not Started | Currently hardcoded lead times
23 | Week 3 | Frontend | Outlet card view toggle | PRD 4.2.2: On outlets list page, add toggle between table view (current) and card view. Each card: outlet name, brand logo, city, status badge, key metrics (rent, CAM, total outflow, area, rent/sqft), revenue input, linked agreements count, risk flags count, next 3 alerts. Quick actions: upload agreement, update payment, add reminder. | P2 MEDIUM | 1 | Not Started
WEEK 4 — CROSS-PORTFOLIO Q&A, TESTING & POLISH
24 | Week 4 | Backend | Cross-Portfolio Q&A (smart dashboard chat) | Phase 2 feature — conversational AI over entire portfolio. POST /api/portfolio-qa with natural language question. Backend converts to SQL query on outlets + agreements + obligations + alerts tables. Examples: 'Which outlets have escalation in next 6 months?', 'What is my total rent exposure in Mumbai?', 'Show me all leases expiring this year'. Use Gemini to generate SQL from question + schema context. Return structured answer. | P1 HIGH | 3 | Not Started | Client's most requested feature
25 | Week 4 | Frontend | Portfolio Q&A chat interface on dashboard | Add chat widget/panel on dashboard page. Input field with suggested questions. Shows AI responses with structured data (tables, lists). Link to relevant outlets/agreements. Save conversation history per session. | P1 HIGH | 1 | Not Started | Companion to backend Q&A
26 | Week 4 | Testing | Backend unit tests (pytest) | Write pytest tests for: (1) extraction pipeline — mock Gemini, verify JSON schema, (2) obligation generation — verify correct obligations from sample extraction, (3) alert generation — verify lead times, (4) payment status logic, (5) role permissions. Target: 80% coverage on core business logic. Add pytest to requirements.txt. | P1 HIGH | 2 | Not Started | Zero tests currently
27 | Week 4 | Testing | Frontend smoke tests | Install Playwright. Write E2E tests for critical flows: (1) Login → Dashboard loads, (2) Upload PDF → Review → Confirm → Outlet created, (3) Outlet detail → all tabs load, (4) Pipeline → drag card between stages, (5) Alerts → acknowledge/snooze. Add test script to package.json. | P1 HIGH | 1 | Not Started
28 | Week 4 | Backend | Split backend into modules | Refactor backend/main.py (2,968 lines) into modules: routes/auth.py, routes/documents.py, routes/outlets.py, routes/agreements.py, routes/payments.py, routes/alerts.py, routes/pipeline.py, routes/showcase.py, routes/reports.py. Shared: services/supabase.py, services/gemini.py, services/notifications.py, models/. Keep main.py as FastAPI app with router includes. | P2 MEDIUM | 1.5 | Not Started | Tech debt — single 3K line file
29 | Week 4 | Infrastructure | Set up monitoring (Sentry + health check) | Add sentry-sdk to backend requirements.txt. Initialize in main.py. Add @sentry_sdk.trace to AI endpoints. Enhance /api/health to check: Supabase connection, Gemini API key valid, storage bucket accessible. Add Sentry to frontend: install @sentry/nextjs, configure in next.config.mjs. | P1 HIGH | 1 | Not Started | Add SENTRY_DSN to both .env files
30 | Week 4 | DevOps | CI/CD pipeline + deployment guide | Create GitHub Actions workflow: (1) On PR: lint + type-check + test, (2) On merge to main: auto-deploy frontend to Vercel, backend to Railway. Write deployment runbook: Supabase setup, env vars, Railway config, Vercel config, DNS. Document in README. | P2 MEDIUM | 0.5 | Not Started
BATCH 5 — GOOGLE CLOUD VISION + ENHANCED Q&A (NEW)
31 | Week 5 | Backend / AI | Integrate Google Cloud Vision API for OCR | Add google-cloud-vision to requirements.txt. Create extract_text_cloud_vision() function in main.py that: (1) Takes list of PIL images, (2) Calls document_text_detection() per page, (3) Returns concatenated full text. Update process_document() flow: scanned PDF → Cloud Vision OCR → if text >= 100 chars → use text path (classify, extract, risk flags via Gemini text mode). Keep Gemini vision as fallback if Cloud Vision fails. Add extraction_method="cloud_vision" to response. | P1 HIGH | 1 | Done | Needs GOOGLE_APPLICATION_CREDENTIALS env var (GCP service account JSON)
32 | Week 5 | Backend / AI | Enhanced single-document Q&A with session history | Update QARequest model to accept session_id. On /api/qa: (1) If session_id provided, fetch prior messages from document_qa_sessions table, (2) Include last 10 messages as conversation history in prompt, (3) Update prompt to require clause citations (blockquotes with section numbers), (4) Save Q&A pair to session after each exchange, return session_id in response. For scanned docs, use Cloud Vision OCR text instead of sending images to Gemini for Q&A. | P1 HIGH | 1.5 | Done | Uses existing document_qa_sessions table from schema.sql
33 | Week 5 | Backend / AI | Cross-portfolio Q&A endpoint | Add POST /api/portfolio-qa endpoint. (1) Accept { question: string }, (2) Use Gemini to generate SELECT SQL from natural language, (3) Provide full DB schema context (outlets, agreements, obligations, alerts, payments), (4) Execute via Supabase RPC exec_readonly_sql, (5) Generate natural language answer from results. Safety: only SELECT allowed, filter by org_id, reject INSERT/UPDATE/DELETE. | P1 HIGH | 1.5 | Done | Needs Supabase RPC function exec_readonly_sql for arbitrary SELECT queries
34 | Week 5 | Frontend | Enhanced Q&A chat panel on agreement detail | Update src/app/agreements/[id]/page.tsx: (1) Persist session_id in state, pass to askDocumentQuestion(), (2) Show conversation history (messages persist across exchanges), (3) Render AI responses with blockquote citations (> quotes styled), (4) Add "Clear conversation" button in header, (5) Add 4 suggested question chips before first message. Update api.ts askDocumentQuestion to accept optional sessionId. | P1 HIGH | 1 | Done
35 | Week 5 | Frontend | Portfolio Q&A widget on dashboard | Add PortfolioQA component to src/app/page.tsx (dashboard): (1) Card with input field, suggested question chips, (2) Expandable message history with user/assistant messages, (3) If response includes data array, render as table (max 10 rows), (4) Loading state with spinner. Add askPortfolioQuestion() to api.ts. | P1 HIGH | 1 | Done
36 | Week 5 | DevOps | Create Supabase RPC function for portfolio Q&A | Create SQL migration for exec_readonly_sql RPC function: CREATE OR REPLACE FUNCTION exec_readonly_sql(query_text text) RETURNS jsonb. Must validate query starts with SELECT, apply org_id filtering via RLS, and return results as JSONB array. Run migration on production Supabase. | P1 HIGH | 0.5 | Not Started | CRITICAL: Must be created in Supabase SQL Editor before portfolio Q&A works
37 | Week 5 | DevOps | Set up GCP service account for Cloud Vision | In Google Cloud Console: (1) Enable Cloud Vision API, (2) Create service account with roles/visionai.user, (3) Download JSON key, (4) Add GOOGLE_APPLICATION_CREDENTIALS to Railway env vars, (5) Test with a scanned PDF upload. Alternative: inline JSON as GOOGLE_CLOUD_VISION_KEY env var. | P1 HIGH | 0.5 | Not Started | Add to Railway backend env vars
TOTAL

## Weekly Plan
GroSpace — 4-Week Sprint Plan
WEEK 1: PRODUCTION HARDENING & INFRASTRUCTURE (Tasks 1-9)
Day(s) | Focus | Details | Priority | Task Ref | Notes
Day 1-2 | Background job system | Set up pg_cron on Supabase. Create 4 Edge Functions: alert-engine, payment-updater, escalation-calculator, email-digest. Test each independently. | P0 CRITICAL | Tasks 1 | Supabase Dashboard → Database → Extensions → Enable pg_cron
Day 2 | Email sending (Resend) | Create Resend account. Add API key. Build email templates. Wire dispatch_notification(). Send test digest. | P0 CRITICAL | Task 2 | resend.com → Get API key → Add to .env
Day 3 | Security hardening | CORS restriction, rate limiting, file size validation, demo creds to env vars. | P0 CRITICAL | Tasks 3-5 | All quick wins, do together
Day 3-4 | Transaction safety | Wrap confirm-and-activate in DB transaction. Test rollback on failure. | P0 CRITICAL | Task 6 | Use Supabase RPC for atomicity
Day 4 | Agreement auto-transitions + Error boundaries | Daily cron updates agreement statuses. Add error.tsx to all routes. | P1 HIGH | Tasks 7-8
Day 5 | Run migration + Week 1 testing | Run migration_004 on prod Supabase. Test all cron jobs. Verify emails send. Fix bugs. | P0 CRITICAL | Task 9 | Test everything end-to-end
WEEK 2: NOTIFICATION CENTER & PHASE 1 COMPLETION (Tasks 10-16)
Day(s) | Focus | Details | Priority | Task Ref | Notes
Day 1-2 | Notification center | Bell icon in top-bar, unread count, slide-out panel, grouped by time, click to navigate. This is the most visible missing feature. | P0 CRITICAL | Task 10 | Use Sheet component from shadcn/ui
Day 2-3 | Split-screen review UI | PDF viewer left + extracted fields right. Confidence badges. Low-confidence auto-expanded. Save as Draft button. | P1 HIGH | Tasks 11-12 | Reuse existing react-pdf component
Day 3-4 | Dashboard enrichment | Add 5 widgets: expiring leases, licenses, risk flags, outlets by model type, outlets by property type. | P1 HIGH | Task 13 | Use recharts (already installed)
Day 4 | Role-scoped dashboards | Different widget sets for platform_admin vs org_admin vs org_member. | P1 HIGH | Task 14 | Use useUser() hook for role check
Day 5 | Agreement timeline + Role enforcement | Horizontal date bar visualization. Backend role permissions middleware. | P1-P2 | Tasks 15-16
WEEK 3: REPORTING, PAYMENTS & WHATSAPP (Tasks 17-23)
Day(s) | Focus | Details | Priority | Task Ref | Notes
Day 1-2 | Complete reports table | All 16 PRD columns. 8 multi-filters. Sortable. CSV with filters applied. This is key for client demos. | P1 HIGH | Task 17 | Most data already available from /api/reports
Day 2 | Bulk payments + calendar view | 'Mark all Paid' button. Monthly obligation calendar grid. | P2 MEDIUM | Task 18
Day 3-4 | WhatsApp via MSG91 | Create MSG91 account. Get approved templates. Wire API. Test with real WhatsApp. | P0 CRITICAL | Task 19 | msg91.com → WhatsApp → Get API key
Day 4 | Rent-to-revenue coloring + MGLR calc | Color code ratios. Implement MAX(MGLR, revenue_share) logic. | P2 MEDIUM | Tasks 20-21
Day 5 | Configurable lead times + Outlet cards | Per-org alert lead times. Card view toggle on outlets page. | P1-P2 | Tasks 22-23
WEEK 4: AI Q&A, TESTING & POLISH (Tasks 24-30)
Day(s) | Focus | Details | Priority | Task Ref | Notes
Day 1-2 | Cross-portfolio Q&A backend | Natural language → SQL generation via Gemini. Schema-aware prompting. Structured responses. | P1 HIGH | Task 24 | Most impactful AI feature
Day 2-3 | Q&A chat UI + polish | Chat widget on dashboard. Suggested questions. Formatted responses with links. | P1 HIGH | Task 25
Day 3-4 | Backend tests (pytest) | Core business logic: extraction, obligations, alerts, payments, permissions. 80% coverage target. | P1 HIGH | Task 26 | Add pytest to requirements.txt
Day 4 | Frontend E2E tests + Backend refactor | Playwright for critical flows. Split main.py into route modules. | P1-P2 | Tasks 27-28
Day 5 | Monitoring + CI/CD + Final QA | Sentry setup. GitHub Actions. Deployment guide. Full regression test. | P1 HIGH | Tasks 29-30 | Ship it!

## Environment Variables
GroSpace — Environment Variables Reference
FRONTEND (.env.local)
Variable / Item | Value / Example | Status | Where to Get
NEXT_PUBLIC_SUPABASE_URL | https://xxxxx.supabase.co | EXISTING | Supabase Dashboard → Settings → API → Project URL
NEXT_PUBLIC_SUPABASE_ANON_KEY | eyJhbGci...your-anon-key | EXISTING | Supabase Dashboard → Settings → API → anon/public key
NEXT_PUBLIC_API_URL | https://grospace-backend.up.railway.app | EXISTING | Railway dashboard → your service → Settings → Domain
NEXT_PUBLIC_APP_URL | https://grospace.vercel.app | EXISTING | Vercel dashboard → your project → Settings → Domains
NEXT_PUBLIC_DEMO_EMAIL | admin@grospace.com | NEW — Week 1 | Move from hardcoded src/app/auth/login/page.tsx
NEXT_PUBLIC_DEMO_PASSWORD | admin2025 | NEW — Week 1 | Move from hardcoded src/app/auth/login/page.tsx
NEXT_PUBLIC_SENTRY_DSN | https://xxx@xxx.ingest.sentry.io/xxx | NEW — Week 4 | sentry.io → Create Project → Next.js → Get DSN
BACKEND (.env)
Variable / Item | Value / Example | Status | Where to Get
SUPABASE_URL | https://xxxxx.supabase.co | EXISTING | Same as frontend SUPABASE_URL
SUPABASE_SERVICE_ROLE_KEY | eyJhbGci...your-service-role-key | EXISTING | Supabase Dashboard → Settings → API → service_role key (SECRET!)
GEMINI_API_KEY | AIza...your-gemini-key | EXISTING | Google AI Studio → Get API Key → makersuite.google.com
FRONTEND_URL | https://grospace.vercel.app | EXISTING | Used for CORS — MUST match actual frontend domain
PORT | 8000 | EXISTING | Railway auto-sets this
RESEND_API_KEY | re_xxxxxxxxxxxx | NEW — Week 1 | resend.com → Sign up → API Keys → Create. Verify domain for production.
RESEND_FROM_EMAIL | alerts@grospace.com | NEW — Week 1 | Must match verified domain in Resend
MSG91_AUTH_KEY | your-msg91-authkey | NEW — Week 3 | msg91.com → Dashboard → Developer → Auth Key
MSG91_SENDER_ID | GROSPC | NEW — Week 3 | msg91.com → WhatsApp → Sender ID (6 chars)
MSG91_WHATSAPP_TEMPLATE_RENT | template-id-for-rent-due | NEW — Week 3 | msg91.com → WhatsApp → Templates → Create & get approved by Meta
MSG91_WHATSAPP_TEMPLATE_EXPIRY | template-id-for-expiry | NEW — Week 3 | msg91.com → WhatsApp → Templates → Create & get approved
SENTRY_DSN | https://xxx@xxx.ingest.sentry.io/xxx | NEW — Week 4 | sentry.io → Create Project → FastAPI → Get DSN
ALLOWED_ORIGINS | https://grospace.vercel.app,http://localhost:3000 | NEW — Week 1 | Comma-separated list of allowed CORS origins
SUPABASE (Dashboard Config — not .env)
Variable / Item | Value / Example | Status | Where to Get
pg_cron extension | Enable in Database → Extensions | NEW — Week 1 | Required for background jobs. Search 'pg_cron' in extensions.
Edge Functions secrets | RESEND_API_KEY, GEMINI_API_KEY | NEW — Week 1 | If using Edge Functions instead of pg_cron for jobs
Storage bucket: documents | Private, 50MB max file size | VERIFY | Storage → documents bucket → Settings → Max file size
Auth: Email confirmations | Enable/disable per environment | VERIFY | Auth → Settings → Email confirmations
Realtime: Enable for alerts | Enable realtime on alerts table | OPTIONAL | Database → alerts table → Enable Realtime
THIRD-PARTY ACCOUNTS NEEDED
Variable / Item | Value / Example | Status | Where to Get
Resend (email) | resend.com | NEW — Week 1 | Free tier: 3,000 emails/month. Add domain DNS records for production.
MSG91 (WhatsApp) | msg91.com | NEW — Week 3 | Indian WhatsApp Business API. Requires business verification by Meta (~2-5 days).
Sentry (monitoring) | sentry.io | NEW — Week 4 | Free tier: 5,000 errors/month. Create org → 2 projects (Next.js + Python).
Railway (backend hosting) | railway.app | EXISTING | Verify: auto-deploy from GitHub main branch enabled.
Vercel (frontend hosting) | vercel.com | EXISTING | Verify: auto-deploy from GitHub main branch enabled.
GOOGLE_APPLICATION_CREDENTIALS | Backend | Path to GCP service account JSON file for Cloud Vision API | /path/to/service-account.json | NEW — Batch 5

## PRD Gap Tracker
GroSpace — PRD Gap Tracker (Phase 1 + Phase 2)
4.1 Document Intelligence
PRD Ref | Gap | Current Status | Planned | Task #
4.1.1 | File size validation (50MB) | PARTIAL | Week 1 | Task 5
4.1.3 | Split-screen review UI | MISSING | Week 2 | Task 11
4.1.3 | Save as Draft option | MISSING | Week 2 | Task 12
4.1.3 | Low-confidence fields auto-expanded | PARTIAL | Week 2 | Task 11
4.1.4 | Q&A conversation persistence | PARTIAL | Week 4 | —
4.2 Outlet Master
PRD Ref | Gap | Current Status | Planned | Task #
4.2.1 | Auto status transitions (operational→renewal) | MISSING | Week 1 | Task 7
4.2.2 | Card view toggle on outlets list | MISSING | Week 3 | Task 23
4.2.3 | Rent-to-revenue color coding | MISSING | Week 3 | Task 20
4.3 Agreement Management
PRD Ref | Gap | Current Status | Planned | Task #
4.3.2 | Agreement timeline visualization | MISSING | Week 2 | Task 15
4.3.1 | Auto status transitions (active→expiring) | MISSING | Week 1 | Task 7
4.4 Obligation Engine
PRD Ref | Gap | Current Status | Planned | Task #
4.4.2 | Escalation auto-recalculation (cron) | MISSING | Week 1 | Task 1
4.4.3 | Hybrid MGLR MAX calculation | MISSING | Week 3 | Task 21
4.5 Payment Tracker
PRD Ref | Gap | Current Status | Planned | Task #
4.5.2 | Bulk 'Mark all Paid' for month | MISSING | Week 3 | Task 18
4.5.2 | Payment calendar view | MISSING | Week 3 | Task 18
4.6 Alert Engine
PRD Ref | Gap | Current Status | Planned | Task #
4.6.1 | Background alert generation (hourly cron) | MISSING | Week 1 | Task 1
4.6.2 | Configurable lead times per org | PARTIAL | Week 3 | Task 22
4.6.3 | Notification center (bell icon + dropdown) | MISSING | Week 2 | Task 10
4.6.4 | Email digest actually sends | MISSING | Week 1 | Task 2
4.7 Dashboard
PRD Ref | Gap | Current Status | Planned | Task #
4.7.1 | Expiring leases/licenses widgets | MISSING | Week 2 | Task 13
4.7.1 | Risk flags summary widget | MISSING | Week 2 | Task 13
4.7.1 | Outlets by model/property type charts | MISSING | Week 2 | Task 13
4.7.2-3 | Role-scoped dashboard views | MISSING | Week 2 | Task 14
4.8 Reporting
PRD Ref | Gap | Current Status | Planned | Task #
4.8.1 | All 16 PRD columns in reports table | PARTIAL | Week 3 | Task 17
4.8.1 | Multi-filter support (8 filters) | MISSING | Week 3 | Task 17
4.8.1 | Sortable columns | MISSING | Week 3 | Task 17
4.8.1 | CSV export with applied filters | PARTIAL | Week 3 | Task 17
4.9 Access Control
PRD Ref | Gap | Current Status | Planned | Task #
4.9.2 | Role permissions matrix enforcement | PARTIAL | Week 2 | Task 16
Phase 2 Features
PRD Ref | Gap | Current Status | Planned | Task #
P2 | Cross-Portfolio Q&A / Smart Dashboard | MISSING | Week 4 | Tasks 24-25
P2 | WhatsApp sending (MSG91) | MISSING | Week 3 | Task 19
P2 | Full Risk Analyzer (configurable per org) | DEFERRED | — | Post 4-week
P2 | Org Viewer role (read-only for investors) | DEFERRED | — | Post 4-week
P2 | Advanced reporting (PDF export, scheduled) | DEFERRED | — | Post 4-week
Production Hardening
PRD Ref | Gap | Current Status | Planned | Task #
INFRA | Background job system (4 cron jobs) | MISSING | Week 1 | Task 1
INFRA | Transaction safety on confirm-and-activate | MISSING | Week 1 | Task 6
INFRA | Error boundaries on all routes | MISSING | Week 1 | Task 8
SEC | CORS restriction | MISSING | Week 1 | Task 3
SEC | Rate limiting on AI endpoints | MISSING | Week 1 | Task 4
TEST | Backend unit tests (pytest) | MISSING | Week 4 | Task 26
TEST | Frontend E2E tests (Playwright) | MISSING | Week 4 | Task 27
OPS | Monitoring (Sentry) | MISSING | Week 4 | Task 29
OPS | CI/CD pipeline | MISSING | Week 4 | Task 30